## Project Status
Project Name |  | BRMS Tech |  | Project Manager |  | Swapnil Wale |  | Date | 2015-01-10
Project Health Card | [7 empty] | Green
Schedule |  | Green | The project tasks are on track.
Budget |  | Green | The budget is on track but some items are a concern.
Resources |  | Amber | The project is well resourced. Some resources have taken unplanned leaves.
Quality |  | Red | There number of unresolved defects has crossed 50.
Scope |  | Amber | The project scope is on track. There are 2 change requests pending.
Risks |  | Amber | Project Risks are under control.
Issues |  | Red | There are 4 high issues open.
Change Mgt |  | Green | The change management plan for the project is being drafted.
Project Schedule
No | Task |  |  | Start | Finish | Progress | Projected Date |  | Concerns
1 | Analysis |  |  | 2015-01-14 | 2015-01-30 | 100 | 2015-01-30 |  | No
2 | Build |  |  | 2015-01-30 | 2015-03-20 | 60 | 2015-01-31 |  | No
3 | Quality Assurance |  |  | 2015-03-25 | 2015-04-30 | 50 | 2015-02-01 |  | No
4 | User Acceptance Testing |  |  | 2015-04-30 | 2015-05-15 | 10 | 2015-02-02 |  | No
5 | Production |  |  | 2015-05-20 | 2015-05-20 | 0 | 2015-02-03 |  | No
6 | Support |  |  | 2015-05-20 | 2015-06-15 | 0 | 2015-02-04 |  | No
Project Financials
No | Item |  |  | Planned Spend |  | Actual Spend |  | Variance
1 | Resourcing Costs |  |  | 450000 |  | 500000 |  | -50000
2 | Software Costs |  |  | 75000 |  | 34000 |  | 41000
3 | Hardware Costs |  |  | 50000 |  | 23000 |  | 27000
4 | Vendor Costs |  |  | 35000 |  | 36000 |  | -1000
5 | Other Expenses |  |  | 5000 |  | 3500 |  | 1500
Totals |  |  |  | 615000 |  | 596500 |  | 18500
Top 5
No | Type | Description |  |  |  | Status | Owner |  | Due
1 | Risk | There is a technical risk with the project which has not been addressed. |  |  |  | Green | Neel |  | 2015-01-12
2 | Issue | Some of the team members have taken unplanned leaves. |  |  |  | Red | Wale |  | 2015-01-14
3 | Decision | A key decision regadring technical architecture is pending. |  |  |  | Amber | Sam |  | 2015-02-23
4 | Dependency | The project has a depedency on other project for hardware which has not been resolved yet. |  |  |  | Green | Ram |  | 2015-04-26
5 | Change Request | The change requests need be approved at the earliest so that the impact on the project is less. |  |  |  | Green | Jam |  | 2015-01-21
Risks |  |  | Issues |  |  | Pending Items

## Data
Status | Items |  | High | Med | Low
Red | Risk | Risks | 5 | 2 | 2
Green | Issue | Issues | 4 | 2 | 3
Amber | Decision
| Action | Decisions | 2
| Dependancy | Actions | 3
| Assumption | Changes | 2
| Change Request | Dependancies | 5